## Roadmap - SEO
|  |  | Client Name: | Hotpoint
|  |  | URL: | https://www.hotpoint.co.uk/
|  |  | Date of last review: | 2026-06-22
Platform:
|  |  | Indexable URLs: | 10604
|  |  | Non-Indexable URLs: | 1028
|  |  | Issues: | 10
|  |  | Warnings: | 4
|  |  | Opportunities: | 5
Status | Group | Issue | Issue Type | Issue Priority | Description | Last Updated | Date Raised | Owner | How to Fix | Date Validated | Supporting Documents | Additional Information
Not Started | Canonicalization | Canonicals: Canonicalised | Warning | High | The URL is 'canonicalised' to another location. This means the search engines are being instructed to not index the page, and the indexing and linking properties should be consolidated to the URL in the canonical. | 2026-06-22 | 2026-06-22 | Hotpoint | These URLs should be reviewed carefully to ensure the indexing and link signals are being consolidated to the correct URL. In a perfect world, a website wouldn't need to canonicalise any URLs as only canonical versions would be linked to internally on a website, but often they are required due to various circumstances outside of control, and to prevent duplicate content. Update internal links to canonical versions of URLs where possible. |  | canonicals_canonicalised
Not Started | Canonicalization | Canonicals: Missing | Warning | Medium | If a page doesn't indicate a canonical URL, Google will identify what they think is the best version or URL. This can lead to ranking unpredictability when there are multiple versions discovered, and hence generally all URLs should specify a canonical version | 2026-06-22 | 2026-06-22 | Hotpoint | Specify a canonical URL for every page to avoid any potential ranking unpredictability if multiple versions of the same page are discovered on different URLs. |  | canonicals_missing
Not Started | Canonicalization | Canonicals: Non-Indexable Canonical | Issue | High | The canonical URL is a non-indexable page. This will include canonicals which are blocked by robots.txt, no response, redirect (3XX), client error (4XX), server error (5XX) or are ‘noindex’. Canonical versions of URLs should always be indexable, ‘200’ response pages. Therefore, canonicals that go to non-indexable pages should be corrected to the resolving indexable versions. | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure that the canonical URL specified in the tag is both valid and indexable. This involves reviewing the canonical URLs to confirm they lead to indexable content and fixing any issues with the referenced pages to ensure they can be crawled and indexed by search engines |  | canonicals_nonindexable_canonical
Not Started | Content | Content: Lorem Ipsum Placeholder | Issue | High | While it's a common practice to use placeholder text such a 'Lorem Ipsum' during the design phase, it's essential to replace such placeholder text with actual, relevant content before publishing the webpage to ensure it ranks well in search engines and provides value to users. | 2026-06-22 | 2026-06-22 | Hotpoint | Replace Lorem Ipsum placeholders with actual, relevant content that provides value to users. |  | content_lorem_ipsum_placeholder
Not Started | Content | Content: Low Content Pages | Opportunity | Medium | Low-content pages refer to webpages that provide minimal value to users or search engines due to their lack of substantial content or meaningful information. Identifying and addressing these pages is important for SEO optimisation, as they can dilute a website's overall quality, potentially leading to lower search engine rankings, and should either be improved with valuable content or removed to enhance the website's SEO performance. | 2026-06-22 | 2026-06-22 | Hotpoint | Enhance the content on those pages with valuable and relevant information or consider moving the content into more comprehensive pages. By ensuring that every page on your website offers substantial value to users and search engines, you can improve SEO performance and user engagement while avoiding issues related to thin or low-quality content. |  | content_low_content_pages
Not Started | H1 | H1: Duplicate | Opportunity | Low | It's important to have distinct, unique and useful main headings. If every page has the same <h1>, then it can make it more challenging for users and the search engines to understand one page from another. | 2026-06-22 | 2026-06-22 | Hotpoint | Update duplicate <h1>s as necessary, so important pages contain a unique and descriptive <h1> for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate. |  | h1_duplicate
Not Started | H1 | H1: Missing | Issue | Medium | The <h1> tag in HTML serves as the primary heading or title of a web page, providing crucial semantic meaning to both search engines and users. Ensuring every page contains a unique <h1> tag not only enhances a website's structure and search engine ranking but also contributes to a user-friendly and future-proofed web design. | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure important pages have concise, descriptive and unique headings to help users, and enable search engines to score and rank the page for relevant search queries. |  | h1_missing
Not Started | H1 | H1: Multiple | Warning | Medium | Multiple H1 tags on a web page can lead to poor SEO and HTML structure, as they are typically meant to represent the main heading of a page. | 2026-06-22 | 2026-06-22 | Hotpoint | To maintain proper page structure and improve search engine optimization, it's important to use H1 tags judiciously and reserve them for the primary topic or title of the page. |  | h1_multiple
Not Started | Meta Description | Meta Description: Duplicate | Opportunity | Low | It's really important to have distinct and unique meta descriptions that communicate the benefits and purpose of each page. If they are duplicate or irrelevant, then they will be ignored by search engines in their snippets. | 2026-06-22 | 2026-06-22 | Hotpoint | Update duplicate meta descriptions as necessary, so important pages contain a unique and descriptive title for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate. |  | meta_description_duplicate
Not Started | Meta Description | Meta Description: Missing | Opportunity | Low | The importance of addressing missing meta descriptions in web content lies in their role as a crucial first impression for potential visitors. Without a carefully crafted meta description, your web pages may appear less appealing in search results, leading to lower click-through rates and missed opportunities to engage with your target audience. | 2026-06-22 | 2026-06-22 | Hotpoint | To fix a missing meta description, simply add a concise and relevant summary of the page's content within the <meta> tag of the HTML document's <head> section. Aim for around 150-160 characters to ensure it displays properly in search engine results and provides a clear preview of your page's content. |  | meta_description_missing
Not Started | Page Titles | Page Titles: Duplicate | Opportunity | Medium | It's really important to have distinct and unique page titles for every page. If every page has the same page title, then it can make it more challenging for users and the search engines to understand one page from another. | 2026-06-22 | 2026-06-22 | Hotpoint | Update duplicate page titles as necessary, so each page contains a unique and descriptive title for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate. |  | page_titles_duplicate
Not Started | Page Titles | Page Titles: Missing | Issue | High | Missing page titles can significantly impact a website's search engine visibility and user experience. | 2026-06-22 | 2026-06-22 | Hotpoint | Each page on the website should have a unique and descriptive page title that accurately represents the content of the page, helping both users and search engines understand its relevance within the site. |  | page_titles_missing
Not Started | Page Titles | Page Titles: Multiple | Issue | High | There should only be a single page title element for a page. Multiple page titles are often caused by multiple conflicting plugins or modules in CMS. | 2026-06-22 | 2026-06-22 | Hotpoint | Eliminate duplicate or conflicting titles and focusing on a concise and descriptive title |  | page_titles_multiple
Not Started | Page Titles | Page Titles: Outside <head> | Issue | High | The page title should be within the head element, or search engines may ignore it. Google will often still recognise the page title even outside of the head element, however this should not be relied upon. | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure that the page titles are placed within the <body> section |  | page_titles_outside_head
Not Started | Page Titles | Page Titles: Same as h1 | Issue | Medium | When page titles are identical to the H1 headings, it can lead to a lack of differentiation between these critical elements, potentially causing confusion for search engines and users about the page's main topic. | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure that page titles and H1 headings are distinct and complementary, with the page title providing a broader context and the H1 tag focusing on the specific topic or main heading, which can help improve both SEO and user experience. |  | page_titles_same_as_h1
Not Started | Pagination | Pagination: Non-Indexable | Warning | High | Generally they should all be indexable, unless there is a ‘view-all’ page set, or there are extra parameters on pagination URLs, and they require canonicalising to a single URL. One of the most common mistakes is canonicalising page 2+ paginated pages to the first page in a series. Google recommend against this implementation because the component pages don’t actually contain duplicate content. Another common mistake is using ‘noindex’, which can mean Google drops paginated URLs from the index completely and stops following outlinks from those pages, which can be a problem for the products on those pages. | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure that each paginated page contains unique and valuable content that warrants indexing. Additionally, use rel="prev" and rel="next" link tags to indicate the relationship between the paginated pages, helping search engines understand the structure and importance of the content sequence, which can improve SEO performance for paginated content. |  | pagination_nonindexable
Not Started | Pagination | Pagination: Pagination URL Not In Anchor Tag | Issue | High | Search engines may not discover or index content hidden behind pagination buttons that lack unique and crawlable URLs | 2026-06-22 | 2026-06-22 | Hotpoint | Ensure that each page in the pagination has its own distinct URL within anchor tags, enabling search engines to properly crawl and index all relevant content. |  | pagination_pagination_url_not_in_anchor_tag
Not Started | Pagination | Pagination: Sequence Error | Issue | Medium | When pagination sequences contain errors, it can disrupt the user experience and hinder search engine crawlability. This can lead to incomplete or incorrect indexing of paginated content. | 2026-06-22 | 2026-06-22 | Hotpoint | Make sure that that pagination sequences are correctly structured, with consistent and logical URLs that allow both users and search engines to navigate paginated content seamlessly. |  | pagination_sequence_error
Not Started | URL | URL: Contains A Space | Issue | Low | Spaces in URLs is discouraged because they can lead to readability issues and compatibility problems with various web browsers and servers. To ensure optimal SEO performance and user accessibility, it's advisable to use hyphens or underscores to separate words in URLs instead of spaces, creating URLs that are more search engine-friendly and user-friendly. | 2026-06-22 | 2026-06-22 | Hotpoint | Replace the spaces with hyphens or underscores. URLs with spaces can lead to encoding issues and are less user-friendly, so using hyphens or underscores not only ensures proper rendering |  | url_contains_space
Note on C75: Custom extraction in Screaming Frog, review output to ensure all pages have a meta viewport with width or initial scale
Note on C120: Manual: Follow multi-step approach to compile a list of URLs that historical redircts should be establsied for.

## Sheet1 (hidden)
[7 empty] | Client Name: | Trend
[7 empty] | URL: | https://trendsettingawards.com/
[7 empty] | Date of review: | 2023-08-16
[7 empty] | Platform: | WordPress
Staus | Group | Issue Name | Issue Type | Issue Priority | Description | How to Fix | Owner | Supporting Documents
Not Started | Structure | Content: Readability Difficult | Opportunity | Low | Copy on the page is difficult to read and best understood by college graduates according to the Flesch reading-ease score formula. Copy that has long sentences and uses complex words are generally harder to read and understand. | Consider improving the readability of copy for your target audience. Copy that uses shorter sentences with less complex words is often easier to read and understand.
|  | H2: Missing | Warning | Low | Pages which have a missing <h2>, the content is empty or has a whitespace. The <h2> heading is often used to describe sections or topics within a document. They act as signposts for the user, and can help search engines understand the page. | Consider using logical and descriptive <h2>s on important pages that help the user and search engines better understand the page.
|  | URL: Parameters | Warning | Low | URLs that include parameters such as '?' or '&'. This isn't an issue for Google or other search engines to crawl unless at significant scale, but it's recommended to limit the number of parameters in a URL which can be complicated for users, and can be a sign of low value-add URLs. | Where possible use a static URL structure without parameters for key indexable URLs. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | Images: Missing Size Attributes | Opportunity | Low | Image elements without dimensions (width and height size attributes) specified in the HTML. This can cause large layout shifts as the page loads and be frustrating experience for users. It is one of the major reasons that contributes to a high Cumulative Layout Shift (CLS). | Define all image sizes as their native size using width and height attributes in the HTML. This allows the browser to calculate enough space for each image before it loads, avoiding large layout shifts.
|  | Meta Description: Below 70 Characters | Opportunity | Low | Pages which have meta descriptions below the configured limit. This isn't strictly an issue, but an opportunity. There is additional room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
|  | Links: Internal Outlinks With No Anchor Text | Opportunity | Low | Pages that have internal links without anchor text or images that are hyperlinked without alt text. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks without anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column is blank, or if an image, the 'Alt Text' column is also blank. Export in bulk via 'Bulk Export > Links > Internal Outlinks With No Anchor Text'. | Review the missing anchor text outlinks and where appropriate include useful and descriptive anchor text to help users and search engines.
|  | Page Titles: Below 30 Characters | Opportunity | Medium | Pages which have page titles under the configured limit. This isn't necessarily an issue, but it does indicate there might be room to target additional keywords or communicate your USPs. | Consider updating the page title to take advantage of the space left to include additional target keywords or USPs.
|  | H2: Over 70 Characters | Opportunity | Low | Pages which have <h2>s over the configured limit. There is no hard limit for characters in an <h2>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h2>s for users, including target keywords where natural for users - without keyword stuffing.
|  | Meta Description: Below 400 Pixels | Opportunity | Low | Pages which have meta descriptions much shorter than Google's estimated pixel length limit. This isn't necessarily an issue, but it does indicate there might be room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
|  | Canonicals: Missing | Warning | Medium | Pages that have no canonical URL present either as a link element, or via HTTP header. If a page doesn't indicate a canonical URL, Google will identify what they think is the best version or URL. This can lead to ranking unpredictability when there are multiple versions discovered, and hence generally all URLs should specify a canonical version | Specify a canonical URL for every page to avoid any potential ranking unpredictability if multiple versions of the same page are discovered on different URLs.
|  | Canonicals: Canonicalised | Warning | High | Pages that have a canonical to a different URL. The URL is 'canonicalised' to another location. This means the search engines are being instructed to not index the page, and the indexing and linking properties should be consolidated to the URL in the canonical. | These URLs should be reviewed carefully to ensure the indexing and link signals are being consolidated to the correct URL. In a perfect world, a website wouldn't need to canonicalise any URLs as only canonical versions would be linked to internally on a website, but often they are required due to various circumstances outside of control, and to prevent duplicate content. Update internal links to canonical versions of URLs where possible.
|  | Security: Missing Content-Security-Policy Header | Warning | Low | URLs that are missing the Content-Security-Policy response header. This header allows a website to control which resources are loaded for a page. This policy can help guard against cross-site scripting (XSS) attacks that exploit the browser's trust of the content received from the server. The SEO Spider only checks for existence of the header, and does not interrogate the policies found within the header to determine whether they are well set-up for the website. This should be performed manually. | Set a strict Content-Security-Policy response header across all page to help mitigate cross site scripting (XSS) and data injection attacks.
|  | H1: Non-Sequential | Warning | Low | Pages with an <h1> that is not the first heading on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h1> is the first heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the first heading level should be an <h1>, and this should be followed by an <h2>.
|  | Page Titles: Over 60 Characters | Opportunity | Medium | Pages which have page titles that exceed the configured limit. Characters over this limit might be truncated in Google's search results and carry less weight in scoring. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
|  | Content: Low Content Pages | Opportunity | Medium | Pages with a word count that is below the default 200 words. The word count is based upon the content area settings used in the analysis which can be configured via 'Config > Content > Area'. There isn't a minimum word count for pages in reality, but the search engines do require descriptive text to understand the purpose of a page. This filter should only be used as a rough guide to help identify pages that might be improved by adding more descriptive content in the context of the website and page's purpose. Some websites, such as ecommerce, will naturally have lower word counts, which can be acceptable if a products details can be communicated efficiently. | Consider including additional descriptive content to help the user and search engines better understand the page.
|  | H2: Multiple | Warning | Low | Pages which have multiple <h2>s. This is not an issue as HTML standards allow multiple <h2>'s when used in a logical hierarchical heading structure. However, this filter can help you quickly scan to review if they are used appropriately. | Ensure <h2>s are used in a logical hierarchical heading structure, and update where appropriate utilising the full heading rank between (h3 - h6) for additional headings.
|  | H2: Duplicate | Opportunity | Low | Pages which have duplicate <h2>s. It's important to have distinct, unique and useful pages. If every page has the same <h2>, then it can make it more challenging for users and the search engines to understand one page from another. | Update duplicate <h2>s as necessary, so important pages contain a unique and descriptive <h2> for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
|  | Security: Protocol-Relative Resource Links | Warning | Low | URLs that load resources such as images, JavaScript and CSS using protocol-relative links. A protocol-relative link is simply a link to a URL without specifying the scheme (for example, //screamingfrog.co.uk). It helps save developers time from having to specify the protocol and lets the browser determine it based upon the current connection to the resource. However, this technique is now an anti-pattern with HTTPS everywhere, and can expose some sites to 'man in the middle' compromises and performance issues | Update any resource links to be absolute links including the scheme (HTTPS) to avoid security and performance issues.
|  | Response Codes: External Client Error (4xx) | Warning | Low | External URLs with a client-side error. This indicates a problem occurred with the URL request and can include responses such as 400 bad request, 403 Forbidden, 404 Page Not Found, 410 Removed, 429 Too Many Requests and more. A 404 'Page Not Found' is the most common, and often referred to as a broken link. View URLs that link to errors using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > External > Client Error (4xx) inlinks'. | All links on a website should ideally resolve to 200 'OK' URLs. Errors such as 404 broken links should be updated so users are taken to the correct URL, or removed. A 403 forbidden error occurs when a web server denies access to the SEO Spider's request and can often be resolved by switching the user-agent to Chrome via 'Config > User-Agent'. If they can be viewed in a browser, then it's often not an issue.
|  | Security: Unsafe Cross-Origin Links | Warning | Low | URLs that link to external websites using the target="_blank" attribute (to open in a new tab), without using rel="noopener" (or rel="noreferrer") at the same time. Using target="_blank" alone leaves those pages exposed to both security and performance issues for some legacy browsers, which are estimated to be below 5% of market share. Setting target="_blank" on <a> elements implicitly provides the same rel behavior as setting rel="noopener" which does not set window.opener for most modern browsers, such as Chrome, Safari, Firefox and Edge. The external links that contain the target="_blank" attribute by itself can be viewed in the 'outlinks' tab and 'target' column. They can be exported alongside the pages they are linked from via 'Bulk Export > Security > Unsafe Cross-Origin Links'. | Consider the benefits of including the rel="noopener" link attribute on any links that contain the target="_blank" attribute to avoid security and performance issues for the users of legacy browsers that may visit the website.
|  | Meta Description: Missing | Opportunity | Low | Pages which have a missing meta description, the content is empty or has a whitespace. This is a missed opportunity to communicate the benefits of your product or service and influence click through rates for important URLs. | It's important to write unique and descriptive meta descriptions on key pages to communicate the purpose of the page to users, and entice them to click on your result over the competition. It can also mean Google use this description for snippets in the search results for some queries, rather than make up their own based upon the content of the page.
|  | H2: Non-Sequential | Warning | Low | Pages with an <h2> that is not the second heading level after the <h1> on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h2> is the second heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the heading element following an <h1> should be an <h2>, rather than an <h3>.
|  | Page Titles: Over 561 Pixels | Opportunity | Medium | Pages which have page titles over Google's estimated pixel length limit for titles in search results. Google snippet length is actually based upon pixels limits, rather than a character length. The SEO Spider tries to match the latest pixel truncation points in the SERPs, but it is an approximation and Google adjusts them frequently. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
|  | Links: Pages With High External Outlinks | Warning | Low | Pages that have a high number of followed external outlinks on them based upon the 'High External Outlinks' preferences under 'Config > Spider > Preferences'. External outlinks are hyperlinks to another subdomain or domain (depending on your configuration). This might be completely valid, such as linking to another part of the same root domain, or linking to other useful websites. External followed outlinks can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks' where the 'Follow' column is 'True'. | Review followed external outlinks to ensure they are to credible, trusted and relevant websites that are useful to your users.
|  | Images: Missing Alt Attribute | Issue | Low | Images that are missing an alt attribute all together. Click the address (URL) of the image and then the 'Image Details' tab in the lower window pane to view which pages have the image on, and are missing alt attributes. All images should contain an alt attribute with descriptive text, or blank when it's a decorative image. | Include alt attributes with descriptive alt text for images to help users and the search engines understand them better. Where possible, decorative images should be provided using CSS background images or alternatively a null (empty) alt text should be provided (alt="") so that they can be ignored by assistive technologies, such as screen readers.
|  | Security: Missing HSTS Header | Warning | Low | URLs that are missing the HSTS response header. The HTTP Strict-Transport-Security response header (HSTS) instructs browsers that it should only be accessed using HTTPS, rather than HTTP. If a website accepts a connection to HTTP, before being redirected to HTTPS, visitors will initially still communicate over HTTP. The HSTS header instructs the browser to never load over HTTP and to automatically convert all requests to HTTPS. | The HSTS header should be used across all pages to instruct the browser that it should always request pages via HTTPS, rather than HTTP.
|  | Security: HTTP URLs | Issue | High | HTTP URLs that are encountered in the crawl. All websites should be secure over HTTPS today on the web. Not only is it important for security, but it's now expected by users. Chrome and other browsers display a 'Not Secure' message against any URLs that are HTTP, or have mixed content issues (where they load insecure resources on them). To view how these URLs were discovered, view their 'inlinks' in the lower window tab. You can also export any pages that link to HTTP URLs via 'Bulk Export > Security > HTTP URLs Inlinks'. | All URLs should be to secure HTTPS pages. Pages should be served over HTTPS, any internal links should be updated to HTTPS versions and HTTP URLs should 301 redirect to HTTPS versions. HTTP URLs identified in this filter that are redirecting to HTTPS versions already should be updated to link to the correct HTTPS versions directly.
|  | Response Codes: Internal Redirection (3xx) | Warning | Low | Internal URLs which redirect to another URL. These will include server-side redirects, such as 301 or 302 redirects (and more). View URLs that link to redirects using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Redirection (3xx) inlinks'. | Ideally all internal links would be to canonical resolving URLs, and avoid linking to URLs that redirect. This reduces latency of redirect hops for users, and enhanced efficiency for search engines.
|  | Security: Missing X-Content-Type-Options Header | Warning | Low | URLs that are missing the 'X-Content-Type-Options' response header with a 'nosniff' value. In the absence of a MIME type, browsers may 'sniff' to guess the content type to interpret it correctly for users. However, this can be exploited by attackers who can try and load malicious code, such as JavaScript via an image they have compromised. | To minimise security issues, the X-Content-Type-Options response header should be supplied and set to 'nosniff'. This instructs browsers to rely only on the Content-Type header and block anything that does not match accurately. This also means the content-type set needs to be accurate.
|  | URL: Over 115 Characters | Opportunity | Low | URLs that are more than the configured length. This is generally not an issue, however research has shown that users prefer shorter, concise URL strings. | Where possible use logical and concise URLs for users and search engines. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | Images: Missing Alt Text | Issue | Low | Images that have an alt attribute, but are missing alt text. Click the address of the image and then the 'Image Details' tab in the lower window pane to view which pages have the image on them, and are missing alt text. Images should have descriptive alternative text about its purpose, which helps the blind and visually impaired, and the search engines understand it and its relevance to the web page. | Include descriptive alt text for images to help users and the search engines understand them better. Where possible, decorative images should be provided using CSS background images or alternatively a null (empty) alt text should be provided (alt="") so that they can be ignored by assistive technologies, such as screen readers.
|  | URL: Uppercase | Warning | Low | URLs that have uppercase characters within them. URLs are case sensitive, so as best practice generally URLs should be lowercase, to avoid any potential mix ups and duplicate URLs. | Ideally lowercase characters should be used for URLs only. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | H1: Over 70 Characters | Opportunity | Low | Pages which have <h1>s over the configured length. There is no hard limit for characters in an <h1>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h1>s for users, including target keywords where natural for users - without keyword stuffing.
|  | Links: Non-Descriptive Anchor Text In Internal Outlinks | Opportunity | Low | Pages that have internal outlinks with anchor text that is not descriptive, such as 'click here' or 'learn more' based upon the preferences under 'Config > Spider > Preferences'. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks with non-descriptive anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column has words such as 'click here', or 'learn more'. Export in bulk via 'Bulk Export > Links > Non-Descriptive Anchor Text In Internal Outlinks'. | Review the non-descriptive anchor text in outlinks and where appropriate update them to include useful and descriptive anchor text to help provide context to both users and search engines.
|  | Response Codes: External No Response | Warning | Low | External URLs with no response returned from the server. Usually due to a malformed URL, connection timeout, connection error, or connection refused. View URLs that link to no responses using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > External > No Response inlinks'. | Malformed URLs should be updated to the correct location and other connection issues can often be resolved by using different user-agents ('Config > User-Agent'), adjusting the crawl speed ('Config > Speed') or disabling firewalls & proxies. If they can be viewed in a browser, then it's often not an issue.
|  | Security: Missing Secure Referrer-Policy Header | Warning | Low | URLs missing 'no-referrer-when-downgrade', 'strict-origin-when-cross-origin', 'no-referrer' or 'strict-origin' policies in the Referrer-Policy header. When using HTTPS, it's important that the URLs do not leak in non-HTTPS requests. This can expose users to 'man in the middle' attacks, as anyone on the network can view them. | Consider setting a referrer policy of strict-origin-when-cross-origin. It retains much of the referrer's usefulness, while mitigating the risk of leaking data cross-origins.
|  | Security: Missing X-Frame-Options Header | Warning | Low | URLs missing an X-Frame-Options response header with a 'DENY' or 'SAMEORIGIN' value. This instructs the browser not to render a page within a frame, iframe, embed or object. This helps avoid 'clickjacking' attacks, where your content is displayed on another web page that is controlled by an attacker. | To minimise security issues, the X-Frame-Options response header should be supplied with a 'DENY' or 'SAMEORIGIN' value.
|  | Response Codes: Internal Client Error (4xx) | Issue | High | Internal URLs with a client-side error. This indicates a problem occurred with the URL request and can include responses such as 400 bad request, 403 Forbidden, 404 Page Not Found, 410 Removed, 429 Too Many Requests and more. A 404 'Page Not Found' is the most common, and often referred to as a broken link. View URLs that link to errors using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Client Error (4xx) inlinks'. | All links on a website should ideally resolve to 200 'OK' URLs. Errors such as a 404 or 410 should be updated to their correct locations, removed and redirected where appropriate. A 403 forbidden error occurs when a web server denies access to the SEO Spider's request and can often be resolved by switching the user-agent to Chrome via 'Config > User-Agent' and crawling again.
|  | URL: Underscores | Opportunity | Low | URLs with underscores, which are not always seen as word separators by search engines. | Ideally hyphens should be used as word separators, rather than underscores. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | 5xx errors | ERROR
|  | 4xx errors | ERROR |  | A 4xx error means that a webpage cannot be accessed. This is usually the result of broken links. These errors prevent users and search engine robots from accessing your webpages, and can negatively affect both user experience and search engine crawlability. This will in turn lead to a drop in traffic driven to your website. Please be aware that crawler may detect a working link as broken if your website blocks our crawler from accessing it. This usually happens due to the following reasons: - DDoS protection system - Overloaded or misconfigured server | If a webpage returns an error, remove all links leading to the error page or replace it with another resource. To identify all pages on your website that contain links to a 4xx page, click "View broken links" next to the error page. If the links reported as 4xx do work when accessed with a browser, you can try either of the following: - Contact your web hosting support team - Instruct search engine robots not to crawl your website too frequently by specifying the "crawl-delay" directive in your robots.txt
|  | Title tag is missing or empty | ERROR
|  | Blocked from crawling | NOTICE
|  | Duplicate title tag | ERROR
|  | Duplicate content | ERROR
|  | Broken internal links | ERROR
|  | Pages not crawled | ERROR
|  | DNS resolution issue | ERROR
|  | We couldn&#39;t open the page?s URL | ERROR
|  | Broken external links | WARNING
|  | Broken internal images | ERROR
|  | Broken external images | WARNING
|  | Duplicate meta descriptions | ERROR
|  | Invalid robots.txt format | ERROR
|  | Invalid sitemap.xml format | ERROR
|  | Incorrect pages found in sitemap.xml | ERROR
|  | www resolve issues | ERROR
|  | Viewport not configured | ERROR
|  | Large HTML page size | ERROR
|  | Missing canonical tags in AMP pages | ERROR
|  | Issues with hreflang values | ERROR
|  | Hreflang conflicts within page source code | ERROR
|  | Issues with incorrect hreflang links | ERROR
|  | Non-secure pages | ERROR
|  | Certificate Expiration | ERROR
|  | Old security protocol version | ERROR
|  | Certificate registered to incorrect name | ERROR
|  | Issues with mixed content | ERROR
|  | Links lead to HTTP pages for HTTPS site | WARNING
|  | Neither canonical URL nor 301 redirect from HTTP homepage | ERROR
|  | Redirect chains and loops | ERROR
|  | AMP Pages with HTML Issues | ERROR
|  | AMP Pages with Style and Layout Issues | ERROR
|  | AMP Pages with Templating Issues | ERROR
|  | Broken canonical URLs | ERROR
|  | Multiple canonical URLs | ERROR
|  | Meta refresh redirects | ERROR
|  | Broken internal JavaScript and CSS files | ERROR
|  | Insecure encryption algorithms | ERROR
|  | Sitemap file too large | ERROR
|  | Malformed links | ERROR
|  | Structured data that contains markup errors | ERROR
|  | Viewport width not set | ERROR
|  | Title element is too short | WARNING
|  | Title element is too long | WARNING
|  | Missing h1 | WARNING
|  | Multiple h1 tags | NOTICE
|  | Duplicate content in h1 and title | WARNING
|  | Missing meta description | WARNING
|  | Too many on-page links | WARNING
|  | Temporary redirects | WARNING
|  | Missing ALT attributes | WARNING
|  | Slow page load speed | ERROR
|  | Low text to HTML ratio | WARNING
|  | Too many URL parameters | WARNING
|  | Missing hreflang and lang attributes | WARNING
|  | Encoding not declared | WARNING
|  | Doctype not declared | WARNING
|  | Low word count | WARNING
|  | Incompatible plugins used | WARNING
|  | Frames used | WARNING
|  | Underscores in URL | WARNING
|  | Nofollow attributes in internal links | WARNING
|  | Sitemap.xml not specified in robots.txt | WARNING
|  | Sitemap.xml not found | WARNING
|  | HTTPS encryption not used | WARNING
|  | No SNI support | WARNING
|  | HTTP URLs in sitemap.xml for HTTPS site | WARNING
|  | Uncompressed pages | WARNING
|  | Disallowed internal resources | WARNING
|  | Uncompressed JavaScript and CSS files | WARNING
|  | Uncached JavaScript and CSS files | WARNING
|  | Too large JavaScript and CSS total size | WARNING
|  | Too many JavaScript and CSS files | WARNING
|  | Unminified JavaScript and CSS files | WARNING
|  | Warning - Too long URLs | WARNING
|  | Too long URLs | NOTICE
|  | Nofollow attributes in external links | NOTICE
|  | Robots.txt not found | NOTICE
|  | Hreflang language mismatch issues | NOTICE
|  | No HSTS support | NOTICE
|  | Orphaned pages (Google Analytics) | NOTICE
|  | Orphaned sitemap pages | NOTICE
|  | Pages have high Document Interactive Time | NOTICE
|  | Blocked by X-Robots-Tag: noindex HTTP header | NOTICE
|  | Disallowed external resources | NOTICE
|  | Broken external JavaScript and CSS files | NOTICE
|  | Page crawl depth | NOTICE
|  | Pages with only one internal link | NOTICE
|  | Permanent redirects | NOTICE
|  | Resources formatted as page links | NOTICE
|  | Links with no anchor text | NOTICE
|  | Links with non-descriptive anchor text | NOTICE
|  | External pages or resources with 403 HTTP status code | NOTICE

## Copy of Sheet1 (hidden)
| TECHNICAL ANALYSIS | [6 empty] | Client Name: | Trend
[8 empty] | URL: | https://trendsettingawards.com/
[8 empty] | Date of review: | 2023-08-16
[8 empty] | Platform: | WordPress
Staus | Group | Sub-Grouping | Issue Name | Issue Type | Issue Priority | Description | How to Fix | Owner | Supporting Documents
Not Started | Structure

## Sheet2 (hidden)
Status | Grouping | Sub-Grouping | Description | Action | Owner | Proposed Benefit | Priority | Supporting Help File
Not Started | Indexation | Crawl Budget Review | 75.5k URLs excluded by ‘noindex’ tag | This is continuing to decline over time, however a review of pages with 'no-index' tag is recommended to see if this should be adjusted to a full Robots.txt block to optimise crawl budget. | Altus Tech Team | Improved indexation and increased discoverability of relevant pages, without wasting crawl budget to retrieve pages, to then follow the noindex directive. | HIGH
Not Started | Indexation | Crawl Budget Review | 10.k URLs crawled but currently not indexed | These URLs include internal search URLs (which some 301 redirect), feed URLs, & CDN error URLs. There are also URLs from the Altus sub-domains which have benefit to search (some of these sub-domains 301 redirect to the main Altus domain - e.g. https://datasolutions.altusgroup.com/ We would recommend a validation check on these in GSC as these aren't relevant indexable URLs. If a sub-domain has no relevancy to search we would also recommend noindexing it, followed by a Robots.txt block. | Altus Tech Team | Improved indexation and increased discoverability of relevant pages, that we wish to be ranked. | HIGH
Not Started | Indexation | XML sitemaps | Non-indexable URLs in sitemap | Remove non-indexable URLs from sitemap | Altus Tech Team | Decrease in resource requirement & ensures no non-vital pages are crawled. | HIGH | Altus Group - Supporting Documents
Not Started | Indexation | Internal linking | Orphan URLs found in xml sitemap but aren't internal linked | As part of the ongoing addition of pages, ensure they are internally linked to relevant resources. Tie to Pillar Content strategy. | Altus Content Team | While the sitemap is a resource to showcase important URLs internal linking is a strengthen to get key pages found so this will be a key factor in get pages indexed. | MEDIUM | https://developer.chrome.com/docs/lighthouse/seo/link-text/Altus Group - Supporting Documents
Not Started | Indexation | Indexable test URLs | 5 indexable test/dev URLs found | Remove relevant test/dev URLs from the xml sitemap | Altus Tech Team | Potential duplicate content issues | MEDIUM | Altus Group - Supporting Documents
Not Started | Markup | Schema Markup | Company Info markup is not present on the site | Incorporating the correct schema markup on specific pages on your site can help to ensure Google and the major search engines can interpret definitive parts of content on your site. | Altus Tech Team | Using schema helps search engines quickly interpret your information and helps search engine recognise the entities on a page and relate them to their Knowledge Graph. | MEDIUM | https://www.semrush.com/blog/schema-markup-for-company-corporations/
Not Started | On-page Elements | Page title duplication | 31 duplicate page titles found | Issues caused by parameter duplication and indexable dev/test URLs. See supporting doc with a list of the dev/test URLs and the parameter issue to be fixed through canonical block as not in Parameter action. | Altus Content Team | Aligned with better SEO performance | MEDIUM | Altus Group - Supporting Documents
Not Started | On-page Elements | Meta descriptions missing | 2 URLs missing meta descriptions | To create unique meta descriptions | Altus Content Team | To improve organic CTR | LOW | Altus Group - Supporting Documents
Not Started | On-page Elements | Meta description duplication | 35 duplicate meta descriptions | To create unique meta descriptions | Altus Content Team | To improve organic CTR | LOW | Altus Group - Supporting Documents
Not Started | On-page Elements | Missing H1 Headings | 491 URLs missing H1 headings | These URLs contain H1 tags which are blank. The majority of these URLs also contain multiple H1 headings through carousels as well as in the copy below that on the page. The blank H1 tags should be removed and only one header should be marked up as H1 | Altus Content Team | To provide better context to search engine crawlers about on-page content | LOW | Altus Group - Supporting Documents
Not Started | On-page Elements | Multiple H1 Headings | 489 URLs with multiple H1 headings | These URLs contain multiple H1 headings through carousels as well as in the copy below that on the page. Only one header should be marked up as H1 | Altus Content Team | To provide better context to search engine crawlers about on-page content | LOW | Altus Group - Supporting Documents
Not Started | On-page Elements | Images over 100kb | 551 images over 100kb | To compress images where possible without impacting image quality | Altus Tech Team | To improve page speed performance | LOW | Altus Group - Supporting Documents Altus Group - Supporting Documents
Not Started | On-page Elements | Images missing alt text | 965 images missing alt text | To add alt text to missing images | Altus Content Team | This text helps screen-reading tools describe images to visually impaired readers and allows search engines to better crawl and rank your website. | LOW | Altus Group - Supporting DocumentsAltus Group - Supporting Documents
Not Started | On-site duplication | Duplication issues based on parameters | There is parameter duplication within the https://www.altusgroup.com/insights/ section of the site | An example is https://www.altusgroup.com/insights/?Insights=Guide& which should be canonical blocked to https://www.altusgroup.com/insights/ | Altus Tech Team | Aligned with better SEO performance | MEDIUM
Not Started | Structure | International Site Structure | This is a vital area for review to ensure various phrases, where country-specific terminology can be targeted independently (where possible). | Three scenairos have been proposed for discussion. 1) Subfolder Creation (e.g. /us /uk) 2) Country Specific Pages 3) Geo-specifc tabs with variations in copy. Tech considerations & feasibility will need scoped. | Altus Tech Team | This would allow country specific targeting, avoid incorrect pages ranking in incorrect regions (where hreflang is implemented) while ensuring authority is maintained.​ | HIGH | https://developers.google.com/search/docs/specialty/international/localized-versions
Not Started | Structure | HREF Lang Implementation | Dependent on the Site Structure approach, the correct implementation of the HREF Lang attribute would be recommended. | Review requirements for HREF implementation and ensure this is implemented in line with target locale and the associated language. | Altus Tech Team | This would allow country specific targeting, avoid incorrect pages ranking in incorrect regions (where hreflang is implemented) while ensuring authority is maintained.​ | HIGH
Not Started | Structure | Language Translation | Currently the onsite language (non-english) content appears to be translated client-side which means it is not indexed. | Review this mechanism and understand if this can be reviewed and shifted to a server-side approach to aid indexation and SEO impact. | Altus Tech Team | This would allow country specific targeting, avoid incorrect pages ranking in incorrect regions (where hreflang is implemented) while ensuring authority is maintained.​ | HIGH
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Reduce initial server response time | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | A slow response time will negatively impact the user’s experience with the website as this is a delay before anything has even began loading anything of the page resulting in a white page, until the server takes the time to respond and begin providing the data of the page. This impacts LCP & FID CWV metrics. | MEDIUM
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Reduce the impact of third-party code | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Third-party code can significantly impact load performance and currently there are a many different examples present such as Hotjar. This impacts LCP & FID metrics. | MEDIUM
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Audit Google Tag Manager | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | With the use of Google Tag Manger on site it would be beneficial to audit the different tags being added to the site and their associated triggers to establish if any performance savings can be made. This impacts LCP & FID CWV metrics. | LOW
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Reduce unused JavaScript | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Any JavaScript that is present on site but is not actively being used should be removed to help increase performance. Even if the JavaScript is asynchronous (i.e. not render-blocking), the code competes for bandwidth with other resources while it's downloading, which has significant performance implications. This impact LCP & FID CWV metrics. | MEDIUM
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Properly size images | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Images served on your page should be appropriately sized. Unnecessarily large images force users to download useless data, impacting their page experience. This impacts the LCP CWV metric. | MEDIUM
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Reduce unused CSS | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Reducing unused CSS can reduce render-blocking behaviour to speed up your page load and improve CWV metrics. This impacts FCP & LCP CWV metrics. | MEDIUM
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Ensure text remains visible during webfont load | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Fonts are often large files that take a while to load. Some browsers hide text until the font loads, causing a flash of invisible text. Fonts used on site may not remain visible during the web font load. This impacts LCP, FID, & CLS CWV metrics. | LOW
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Enable text compression | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Text-based resources should be served with compression (gzip, deflate or brotli) to minimise total network bytes. Enabling text compression allows you to serve smaller text-based resources, essentially reducing the file size/payload of these resources, in turn decreasing the amount of data transferred. This impacts LCP & FID CWV metrics. | HIGH
Not Started | Technical Optimisation | Core Web Vitals / Page Speed | Serve static assets with an efficient cache policy | Please see accompanying 'Core Web Vitals Audit' document | Altus Tech Team | Serving static assets with an efficient cache policy helps improve page load times on repeat visits by storing these files locally in the user's browser. This impacts LCP & FID CWV metrics. | HIGH
Not Started | Technical Optimisation | Internal redirects | 33 internal 301 redirects | To update internal links to the correct URLs where possible | Altus Tech Team | This helps how crawl efficiency. When search engines rawl your website, they follow internal links to discover and index your pages. By updating internal redirects, you can ensure that search engines can efficiently crawl and index your site's content. Broken or outdated redirects can hinder the crawling process and prevent search engines from reaching important pages on your website. | LOW | Altus Group - Supporting Documents
Not Started | Technical Optimisation | 404 Error Messages | 22k Affected Pages across all sub-domains | Many of these URLs include search/{search_term_string}. To greatly reduce this number a wildcard redirect could be set up to 301 redirect to the main site homepage. | Altus Tech Team | Fixing URLs that return 404 status codes is crucial for providing a positive user experience, preserving link equity, optimising indexing efficiency, and avoiding issues related to confusion and duplicate content. | LOW
Not Started | Technical Optimisation | Parameter Handling | URLs currently resolved with parameters associated with them e.g. https://www.altusgroup.com/services/?s=anything-here. Note this is causing a large amount of duplication issues in the https://www.altusgroup.com/insights/ section of the site | These currently don't redirect, canonicalise or have any form of access block and therefore are creating some additional crawl budget issues. Recommendation is a review of how these are handled, minimum is a canonical implemention, if not a 301 on parameters. | Altus Tech Team | Crawl bloat issues and duplication potenital. | MEDIUM
Not Started | Redirection | Domains | There are several domains, which look like they are part of the Altus group which currently don't resolve but have some levels of value / link equity. e.g http://altusgrouplimited.com/ and http://thealtusgroup.com/ | We would recommend where possible redirecting these with 301 redirects into the AltusGroup.com domain, if there are specific domains related to the 4 core functions of the group, we would suggest redirecting these deep into that area of the site to drive the value directly into that part of the domain, | Altus Tech Team | Pool all historical domain and link authority into the master domain. | LOW

## Copy of Sheet1 1 (hidden)
[7 empty] | Client Name: | Trend
[7 empty] | URL: | https://trendsettingawards.com/
[7 empty] | Date of review: | 2023-08-16
[7 empty] | Platform: | WordPress
Staus | Group | Issue Name | Issue Type | Issue Priority | Description | How to Fix | Owner | Supporting Documents
Not Started | Structure | Content: Readability Difficult | Opportunity | Low | Copy on the page is difficult to read and best understood by college graduates according to the Flesch reading-ease score formula. Copy that has long sentences and uses complex words are generally harder to read and understand. | Consider improving the readability of copy for your target audience. Copy that uses shorter sentences with less complex words is often easier to read and understand.
|  | H2: Missing | Warning | Low | Pages which have a missing <h2>, the content is empty or has a whitespace. The <h2> heading is often used to describe sections or topics within a document. They act as signposts for the user, and can help search engines understand the page. | Consider using logical and descriptive <h2>s on important pages that help the user and search engines better understand the page.
|  | URL: Parameters | Warning | Low | URLs that include parameters such as '?' or '&'. This isn't an issue for Google or other search engines to crawl unless at significant scale, but it's recommended to limit the number of parameters in a URL which can be complicated for users, and can be a sign of low value-add URLs. | Where possible use a static URL structure without parameters for key indexable URLs. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | Images: Missing Size Attributes | Opportunity | Low | Image elements without dimensions (width and height size attributes) specified in the HTML. This can cause large layout shifts as the page loads and be frustrating experience for users. It is one of the major reasons that contributes to a high Cumulative Layout Shift (CLS). | Define all image sizes as their native size using width and height attributes in the HTML. This allows the browser to calculate enough space for each image before it loads, avoiding large layout shifts.
|  | Meta Description: Below 70 Characters | Opportunity | Low | Pages which have meta descriptions below the configured limit. This isn't strictly an issue, but an opportunity. There is additional room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
|  | Links: Internal Outlinks With No Anchor Text | Opportunity | Low | Pages that have internal links without anchor text or images that are hyperlinked without alt text. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks without anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column is blank, or if an image, the 'Alt Text' column is also blank. Export in bulk via 'Bulk Export > Links > Internal Outlinks With No Anchor Text'. | Review the missing anchor text outlinks and where appropriate include useful and descriptive anchor text to help users and search engines.
|  | Page Titles: Below 30 Characters | Opportunity | Medium | Pages which have page titles under the configured limit. This isn't necessarily an issue, but it does indicate there might be room to target additional keywords or communicate your USPs. | Consider updating the page title to take advantage of the space left to include additional target keywords or USPs.
|  | H2: Over 70 Characters | Opportunity | Low | Pages which have <h2>s over the configured limit. There is no hard limit for characters in an <h2>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h2>s for users, including target keywords where natural for users - without keyword stuffing.
|  | Meta Description: Below 400 Pixels | Opportunity | Low | Pages which have meta descriptions much shorter than Google's estimated pixel length limit. This isn't necessarily an issue, but it does indicate there might be room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
|  | Canonicals: Missing | Warning | Medium | Pages that have no canonical URL present either as a link element, or via HTTP header. If a page doesn't indicate a canonical URL, Google will identify what they think is the best version or URL. This can lead to ranking unpredictability when there are multiple versions discovered, and hence generally all URLs should specify a canonical version | Specify a canonical URL for every page to avoid any potential ranking unpredictability if multiple versions of the same page are discovered on different URLs.
|  | Canonicals: Canonicalised | Warning | High | Pages that have a canonical to a different URL. The URL is 'canonicalised' to another location. This means the search engines are being instructed to not index the page, and the indexing and linking properties should be consolidated to the URL in the canonical. | These URLs should be reviewed carefully to ensure the indexing and link signals are being consolidated to the correct URL. In a perfect world, a website wouldn't need to canonicalise any URLs as only canonical versions would be linked to internally on a website, but often they are required due to various circumstances outside of control, and to prevent duplicate content. Update internal links to canonical versions of URLs where possible.
|  | Security: Missing Content-Security-Policy Header | Warning | Low | URLs that are missing the Content-Security-Policy response header. This header allows a website to control which resources are loaded for a page. This policy can help guard against cross-site scripting (XSS) attacks that exploit the browser's trust of the content received from the server. The SEO Spider only checks for existence of the header, and does not interrogate the policies found within the header to determine whether they are well set-up for the website. This should be performed manually. | Set a strict Content-Security-Policy response header across all page to help mitigate cross site scripting (XSS) and data injection attacks.
|  | H1: Non-Sequential | Warning | Low | Pages with an <h1> that is not the first heading on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h1> is the first heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the first heading level should be an <h1>, and this should be followed by an <h2>.
|  | Page Titles: Over 60 Characters | Opportunity | Medium | Pages which have page titles that exceed the configured limit. Characters over this limit might be truncated in Google's search results and carry less weight in scoring. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
|  | Content: Low Content Pages | Opportunity | Medium | Pages with a word count that is below the default 200 words. The word count is based upon the content area settings used in the analysis which can be configured via 'Config > Content > Area'. There isn't a minimum word count for pages in reality, but the search engines do require descriptive text to understand the purpose of a page. This filter should only be used as a rough guide to help identify pages that might be improved by adding more descriptive content in the context of the website and page's purpose. Some websites, such as ecommerce, will naturally have lower word counts, which can be acceptable if a products details can be communicated efficiently. | Consider including additional descriptive content to help the user and search engines better understand the page.
|  | H2: Multiple | Warning | Low | Pages which have multiple <h2>s. This is not an issue as HTML standards allow multiple <h2>'s when used in a logical hierarchical heading structure. However, this filter can help you quickly scan to review if they are used appropriately. | Ensure <h2>s are used in a logical hierarchical heading structure, and update where appropriate utilising the full heading rank between (h3 - h6) for additional headings.
|  | H2: Duplicate | Opportunity | Low | Pages which have duplicate <h2>s. It's important to have distinct, unique and useful pages. If every page has the same <h2>, then it can make it more challenging for users and the search engines to understand one page from another. | Update duplicate <h2>s as necessary, so important pages contain a unique and descriptive <h2> for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
|  | Security: Protocol-Relative Resource Links | Warning | Low | URLs that load resources such as images, JavaScript and CSS using protocol-relative links. A protocol-relative link is simply a link to a URL without specifying the scheme (for example, //screamingfrog.co.uk). It helps save developers time from having to specify the protocol and lets the browser determine it based upon the current connection to the resource. However, this technique is now an anti-pattern with HTTPS everywhere, and can expose some sites to 'man in the middle' compromises and performance issues | Update any resource links to be absolute links including the scheme (HTTPS) to avoid security and performance issues.
|  | Response Codes: External Client Error (4xx) | Warning | Low | External URLs with a client-side error. This indicates a problem occurred with the URL request and can include responses such as 400 bad request, 403 Forbidden, 404 Page Not Found, 410 Removed, 429 Too Many Requests and more. A 404 'Page Not Found' is the most common, and often referred to as a broken link. View URLs that link to errors using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > External > Client Error (4xx) inlinks'. | All links on a website should ideally resolve to 200 'OK' URLs. Errors such as 404 broken links should be updated so users are taken to the correct URL, or removed. A 403 forbidden error occurs when a web server denies access to the SEO Spider's request and can often be resolved by switching the user-agent to Chrome via 'Config > User-Agent'. If they can be viewed in a browser, then it's often not an issue.
|  | Security: Unsafe Cross-Origin Links | Warning | Low | URLs that link to external websites using the target="_blank" attribute (to open in a new tab), without using rel="noopener" (or rel="noreferrer") at the same time. Using target="_blank" alone leaves those pages exposed to both security and performance issues for some legacy browsers, which are estimated to be below 5% of market share. Setting target="_blank" on <a> elements implicitly provides the same rel behavior as setting rel="noopener" which does not set window.opener for most modern browsers, such as Chrome, Safari, Firefox and Edge. The external links that contain the target="_blank" attribute by itself can be viewed in the 'outlinks' tab and 'target' column. They can be exported alongside the pages they are linked from via 'Bulk Export > Security > Unsafe Cross-Origin Links'. | Consider the benefits of including the rel="noopener" link attribute on any links that contain the target="_blank" attribute to avoid security and performance issues for the users of legacy browsers that may visit the website.
|  | Meta Description: Missing | Opportunity | Low | Pages which have a missing meta description, the content is empty or has a whitespace. This is a missed opportunity to communicate the benefits of your product or service and influence click through rates for important URLs. | It's important to write unique and descriptive meta descriptions on key pages to communicate the purpose of the page to users, and entice them to click on your result over the competition. It can also mean Google use this description for snippets in the search results for some queries, rather than make up their own based upon the content of the page.
|  | H2: Non-Sequential | Warning | Low | Pages with an <h2> that is not the second heading level after the <h1> on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h2> is the second heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the heading element following an <h1> should be an <h2>, rather than an <h3>.
|  | Page Titles: Over 561 Pixels | Opportunity | Medium | Pages which have page titles over Google's estimated pixel length limit for titles in search results. Google snippet length is actually based upon pixels limits, rather than a character length. The SEO Spider tries to match the latest pixel truncation points in the SERPs, but it is an approximation and Google adjusts them frequently. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
|  | Links: Pages With High External Outlinks | Warning | Low | Pages that have a high number of followed external outlinks on them based upon the 'High External Outlinks' preferences under 'Config > Spider > Preferences'. External outlinks are hyperlinks to another subdomain or domain (depending on your configuration). This might be completely valid, such as linking to another part of the same root domain, or linking to other useful websites. External followed outlinks can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks' where the 'Follow' column is 'True'. | Review followed external outlinks to ensure they are to credible, trusted and relevant websites that are useful to your users.
|  | Images: Missing Alt Attribute | Issue | Low | Images that are missing an alt attribute all together. Click the address (URL) of the image and then the 'Image Details' tab in the lower window pane to view which pages have the image on, and are missing alt attributes. All images should contain an alt attribute with descriptive text, or blank when it's a decorative image. | Include alt attributes with descriptive alt text for images to help users and the search engines understand them better. Where possible, decorative images should be provided using CSS background images or alternatively a null (empty) alt text should be provided (alt="") so that they can be ignored by assistive technologies, such as screen readers.
|  | Security: Missing HSTS Header | Warning | Low | URLs that are missing the HSTS response header. The HTTP Strict-Transport-Security response header (HSTS) instructs browsers that it should only be accessed using HTTPS, rather than HTTP. If a website accepts a connection to HTTP, before being redirected to HTTPS, visitors will initially still communicate over HTTP. The HSTS header instructs the browser to never load over HTTP and to automatically convert all requests to HTTPS. | The HSTS header should be used across all pages to instruct the browser that it should always request pages via HTTPS, rather than HTTP.
|  | Security: HTTP URLs | Issue | High | HTTP URLs that are encountered in the crawl. All websites should be secure over HTTPS today on the web. Not only is it important for security, but it's now expected by users. Chrome and other browsers display a 'Not Secure' message against any URLs that are HTTP, or have mixed content issues (where they load insecure resources on them). To view how these URLs were discovered, view their 'inlinks' in the lower window tab. You can also export any pages that link to HTTP URLs via 'Bulk Export > Security > HTTP URLs Inlinks'. | All URLs should be to secure HTTPS pages. Pages should be served over HTTPS, any internal links should be updated to HTTPS versions and HTTP URLs should 301 redirect to HTTPS versions. HTTP URLs identified in this filter that are redirecting to HTTPS versions already should be updated to link to the correct HTTPS versions directly.
|  | Response Codes: Internal Redirection (3xx) | Warning | Low | Internal URLs which redirect to another URL. These will include server-side redirects, such as 301 or 302 redirects (and more). View URLs that link to redirects using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Redirection (3xx) inlinks'. | Ideally all internal links would be to canonical resolving URLs, and avoid linking to URLs that redirect. This reduces latency of redirect hops for users, and enhanced efficiency for search engines.
|  | Security: Missing X-Content-Type-Options Header | Warning | Low | URLs that are missing the 'X-Content-Type-Options' response header with a 'nosniff' value. In the absence of a MIME type, browsers may 'sniff' to guess the content type to interpret it correctly for users. However, this can be exploited by attackers who can try and load malicious code, such as JavaScript via an image they have compromised. | To minimise security issues, the X-Content-Type-Options response header should be supplied and set to 'nosniff'. This instructs browsers to rely only on the Content-Type header and block anything that does not match accurately. This also means the content-type set needs to be accurate.
|  | URL: Over 115 Characters | Opportunity | Low | URLs that are more than the configured length. This is generally not an issue, however research has shown that users prefer shorter, concise URL strings. | Where possible use logical and concise URLs for users and search engines. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | Images: Missing Alt Text | Issue | Low | Images that have an alt attribute, but are missing alt text. Click the address of the image and then the 'Image Details' tab in the lower window pane to view which pages have the image on them, and are missing alt text. Images should have descriptive alternative text about its purpose, which helps the blind and visually impaired, and the search engines understand it and its relevance to the web page. | Include descriptive alt text for images to help users and the search engines understand them better. Where possible, decorative images should be provided using CSS background images or alternatively a null (empty) alt text should be provided (alt="") so that they can be ignored by assistive technologies, such as screen readers.
|  | URL: Uppercase | Warning | Low | URLs that have uppercase characters within them. URLs are case sensitive, so as best practice generally URLs should be lowercase, to avoid any potential mix ups and duplicate URLs. | Ideally lowercase characters should be used for URLs only. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | H1: Over 70 Characters | Opportunity | Low | Pages which have <h1>s over the configured length. There is no hard limit for characters in an <h1>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h1>s for users, including target keywords where natural for users - without keyword stuffing.
|  | Links: Non-Descriptive Anchor Text In Internal Outlinks | Opportunity | Low | Pages that have internal outlinks with anchor text that is not descriptive, such as 'click here' or 'learn more' based upon the preferences under 'Config > Spider > Preferences'. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks with non-descriptive anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column has words such as 'click here', or 'learn more'. Export in bulk via 'Bulk Export > Links > Non-Descriptive Anchor Text In Internal Outlinks'. | Review the non-descriptive anchor text in outlinks and where appropriate update them to include useful and descriptive anchor text to help provide context to both users and search engines.
|  | Response Codes: External No Response | Warning | Low | External URLs with no response returned from the server. Usually due to a malformed URL, connection timeout, connection error, or connection refused. View URLs that link to no responses using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > External > No Response inlinks'. | Malformed URLs should be updated to the correct location and other connection issues can often be resolved by using different user-agents ('Config > User-Agent'), adjusting the crawl speed ('Config > Speed') or disabling firewalls & proxies. If they can be viewed in a browser, then it's often not an issue.
|  | Security: Missing Secure Referrer-Policy Header | Warning | Low | URLs missing 'no-referrer-when-downgrade', 'strict-origin-when-cross-origin', 'no-referrer' or 'strict-origin' policies in the Referrer-Policy header. When using HTTPS, it's important that the URLs do not leak in non-HTTPS requests. This can expose users to 'man in the middle' attacks, as anyone on the network can view them. | Consider setting a referrer policy of strict-origin-when-cross-origin. It retains much of the referrer's usefulness, while mitigating the risk of leaking data cross-origins.
|  | Security: Missing X-Frame-Options Header | Warning | Low | URLs missing an X-Frame-Options response header with a 'DENY' or 'SAMEORIGIN' value. This instructs the browser not to render a page within a frame, iframe, embed or object. This helps avoid 'clickjacking' attacks, where your content is displayed on another web page that is controlled by an attacker. | To minimise security issues, the X-Frame-Options response header should be supplied with a 'DENY' or 'SAMEORIGIN' value.
|  | Response Codes: Internal Client Error (4xx) | Issue | High | Internal URLs with a client-side error. This indicates a problem occurred with the URL request and can include responses such as 400 bad request, 403 Forbidden, 404 Page Not Found, 410 Removed, 429 Too Many Requests and more. A 404 'Page Not Found' is the most common, and often referred to as a broken link. View URLs that link to errors using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Client Error (4xx) inlinks'. | All links on a website should ideally resolve to 200 'OK' URLs. Errors such as a 404 or 410 should be updated to their correct locations, removed and redirected where appropriate. A 403 forbidden error occurs when a web server denies access to the SEO Spider's request and can often be resolved by switching the user-agent to Chrome via 'Config > User-Agent' and crawling again.
|  | URL: Underscores | Opportunity | Low | URLs with underscores, which are not always seen as word separators by search engines. | Ideally hyphens should be used as word separators, rather than underscores. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
|  | 5xx errors | ERROR
|  | 4xx errors | ERROR |  | A 4xx error means that a webpage cannot be accessed. This is usually the result of broken links. These errors prevent users and search engine robots from accessing your webpages, and can negatively affect both user experience and search engine crawlability. This will in turn lead to a drop in traffic driven to your website. Please be aware that crawler may detect a working link as broken if your website blocks our crawler from accessing it. This usually happens due to the following reasons: - DDoS protection system - Overloaded or misconfigured server | If a webpage returns an error, remove all links leading to the error page or replace it with another resource. To identify all pages on your website that contain links to a 4xx page, click "View broken links" next to the error page. If the links reported as 4xx do work when accessed with a browser, you can try either of the following: - Contact your web hosting support team - Instruct search engine robots not to crawl your website too frequently by specifying the "crawl-delay" directive in your robots.txt
|  | Title tag is missing or empty | ERROR
|  | Blocked from crawling | NOTICE
|  | Duplicate title tag | ERROR
|  | Duplicate content | ERROR
|  | Broken internal links | ERROR
|  | Pages not crawled | ERROR
|  | DNS resolution issue | ERROR
|  | We couldn&#39;t open the page?s URL | ERROR
|  | Broken external links | WARNING
|  | Broken internal images | ERROR
|  | Broken external images | WARNING
|  | Duplicate meta descriptions | ERROR
|  | Invalid robots.txt format | ERROR
|  | Invalid sitemap.xml format | ERROR
|  | Incorrect pages found in sitemap.xml | ERROR
|  | www resolve issues | ERROR
|  | Viewport not configured | ERROR
|  | Large HTML page size | ERROR
|  | Missing canonical tags in AMP pages | ERROR
|  | Issues with hreflang values | ERROR
|  | Hreflang conflicts within page source code | ERROR
|  | Issues with incorrect hreflang links | ERROR
|  | Non-secure pages | ERROR
|  | Certificate Expiration | ERROR
|  | Old security protocol version | ERROR
|  | Certificate registered to incorrect name | ERROR
|  | Issues with mixed content | ERROR
|  | Links lead to HTTP pages for HTTPS site | WARNING
|  | Neither canonical URL nor 301 redirect from HTTP homepage | ERROR
|  | Redirect chains and loops | ERROR
|  | AMP Pages with HTML Issues | ERROR
|  | AMP Pages with Style and Layout Issues | ERROR
|  | AMP Pages with Templating Issues | ERROR
|  | Broken canonical URLs | ERROR
|  | Multiple canonical URLs | ERROR
|  | Meta refresh redirects | ERROR
|  | Broken internal JavaScript and CSS files | ERROR
|  | Insecure encryption algorithms | ERROR
|  | Sitemap file too large | ERROR
|  | Malformed links | ERROR
|  | Structured data that contains markup errors | ERROR
|  | Viewport width not set | ERROR
|  | Title element is too short | WARNING
|  | Title element is too long | WARNING
|  | Missing h1 | WARNING
|  | Multiple h1 tags | NOTICE
|  | Duplicate content in h1 and title | WARNING
|  | Missing meta description | WARNING
|  | Too many on-page links | WARNING
|  | Temporary redirects | WARNING
|  | Missing ALT attributes | WARNING
|  | Slow page load speed | ERROR
|  | Low text to HTML ratio | WARNING
|  | Too many URL parameters | WARNING
|  | Missing hreflang and lang attributes | WARNING
|  | Encoding not declared | WARNING
|  | Doctype not declared | WARNING
|  | Low word count | WARNING
|  | Incompatible plugins used | WARNING
|  | Frames used | WARNING
|  | Underscores in URL | WARNING
|  | Nofollow attributes in internal links | WARNING
|  | Sitemap.xml not specified in robots.txt | WARNING
|  | Sitemap.xml not found | WARNING
|  | HTTPS encryption not used | WARNING
|  | No SNI support | WARNING
|  | HTTP URLs in sitemap.xml for HTTPS site | WARNING
|  | Uncompressed pages | WARNING
|  | Disallowed internal resources | WARNING
|  | Uncompressed JavaScript and CSS files | WARNING
|  | Uncached JavaScript and CSS files | WARNING
|  | Too large JavaScript and CSS total size | WARNING
|  | Too many JavaScript and CSS files | WARNING
|  | Unminified JavaScript and CSS files | WARNING
|  | Warning - Too long URLs | WARNING
|  | Too long URLs | NOTICE
|  | Nofollow attributes in external links | NOTICE
|  | Robots.txt not found | NOTICE
|  | Hreflang language mismatch issues | NOTICE
|  | No HSTS support | NOTICE
|  | Orphaned pages (Google Analytics) | NOTICE
|  | Orphaned sitemap pages | NOTICE
|  | Pages have high Document Interactive Time | NOTICE
|  | Blocked by X-Robots-Tag: noindex HTTP header | NOTICE
|  | Disallowed external resources | NOTICE
|  | Broken external JavaScript and CSS files | NOTICE
|  | Page crawl depth | NOTICE
|  | Pages with only one internal link | NOTICE
|  | Permanent redirects | NOTICE
|  | Resources formatted as page links | NOTICE
|  | Links with no anchor text | NOTICE
|  | Links with non-descriptive anchor text | NOTICE
|  | External pages or resources with 403 HTTP status code | NOTICE